Project Initiation Document

http://admin.exeter.ac.uk/corporate/campus-services/retail-services/selfserviceprint/

Document Control

| Project Title: | Self Service Printing and Copying (SSPC) |
| --- | --- |
| Project Manager: | Phil Rees-Jones |
| Date: | November 26th 2009 |

| Version | Date | Author(s) | Notes on Revisions |
| --- | --- | --- | --- |
| V1 | Nov 25 | P R-J |  |
| V2 | Dec 10 | P R-J |  |
| V3 | Jan 10 | P R-J |  |
| V4 | Jan 10 | P R-J |  |
| V5 | Jan 10 | P R-J |  |
| V6 | Jan 10 | P R-J |  |
| V7 | Jan 10 | P R-J |  |
| V8 | Jan 10 | P R-J |  |
| V9 | Feb 10 | P R-J |  |
| V10 | Apr 10 | P R-J |  |
| V11 | May 10 | P R-J |  |

| Proposal Produced | If yes date of meeting submitted | Meeting submitted to: |
| --- | --- | --- |
| YES |  | PCG |

Consultation with:

| Date | Person | Service/School |
| --- | --- | --- |
|  | Phil Rees-Jones | Chair. Representative of the Lead Department. |
|  | Richard Price | Contracts Officer, Procurement |
|  | Steve Grange & Pete Bishop | ICSD- Head of IT Infrastructure PALMS PC Clusters |
|  | Roger Snelling | Head of Networks- The use of the network |
|  | Stephen Mossop | Head of Library Services- Cashcard replacement. |
|  | Martin Henson | Finance & Systems team, Corporate Services Recharging and Finance |
|  | Nigel Phillips | Print Services Manager Nigel Phillips is the technical adviser. |
|  | Julie Brown | Asst Implementation Manager Campus Services |
|  | Paul Lightowlers | Head of Software Support |
|  | Geoff Pringle | CaS Director |
|  | John Malloch | Head of Procurement |
|  | Jilly Court | CaS Deputy Director |
|  | Mike Walton | Assistant Director Academic Services & Project Board Member |
|  | Deborah Welland | Assistant Director BISS |
|  | Julian Vinnels | IT Services Manager PCMD |
|  | Anna Verhamme | Change Manager / College Manager (Business School) |
|  | Richard King | HUSS IT Asst |
|  | Nigel Weaver | St Lukes |
|  | Various Solution Suppliers |  |
|  | University cross sector colleagues |  |
|  | Dick Leitch | Senior Project Manager |
|  | Barry Clark | CS Business Services Manager |

Table of Contents

1.	Project Overview	3

2.	PROJect objectives	3

2.1.	Metrics	3

2.2	SUSTAINABILITY ISSUES	3

2.3	Data Protection	3

3.	Scope & Timescale of the Project	3

3.1	Related Projects	3

3.2	Out of Scope	3

4.	RISKS, constraints and ASSUMPTIONS	3

4.1	Risks	3

4.2	Constraints & Dependencies	3

4.3	Assumptions	3

5.	ReSource for the Project	3

5.1	Finance	3

5.2	Staffing Resources	3

6.	Managing the Project	3

6.1	Issue Control	3

6.2  	Actions Register	3

6.3	Financial Control	3

6.4	Information Management	3

7.	stakeholders	3

8.	planning	3

9.	APPROVAL	3

# Project Overview

The departments of the University operate about 115 copiers and multi-functional devices (MFD) (printer-scanner-photocopiers) and many desktop printers of many different types all using electricity (often around the clock), cartridges and maintenance support.  The University in 2008/09 spent more than £176k on MFD printing, over £100k on printer cartridges, at least £500k on paper, £400k on external printing (prospectuses and similar) and an unknown amount on computer printer purchase.  One science school has 99 printers of 50 different types and one room in Northcote House has 4 occupants with 4 desktop printers, a fax machine and a scanner. These numbers are fairly representative.  The number of individual scanners and fax machines is, so far, unknown but certainly significant. The equipment survey planned for August 2010 will provide a robust report of the quantity of MFD’s, printers, scanners, desktop printers etc on campuses (Streatham and St Lukes)  This arrangement has developed in a piecemeal way.  The result is inefficient, costly and does not provide the modern service expected by users.

Southern Universities Management Services (SUMS) recently reviewed the University’s printing and copying facilities and presented its findings and conclusions in report number 1137/09, which was approved by the Technical Infrastructure Group (TIG) on 10 Sep 09.

The Creating Value Group (CVG) has approved the improvement of the self-service printing and copying service to produce savings and efficiencies.

# PROJect objectives

  - The main deliverables of the project are:

- A single contract with one supplier for a ‘managed print service’, under which all MFDs, selected desktop printers and print-management software are supported by that supplier.  Support includes implementation management, advice, replacement toner cartridges, repair, maintenance, selection and provision of new machines, management information, continuous improvement and so on.  Campus Services will lead the provision of the service by providing the service manager.

- A universal approach to self-service P&C at the Streatham, St. Luke’s and Cornish (ASU) campuses, and for associated organisations such as TCS, TDV, PCMD, GWR and the Guild that choose to participate.

- The replacement of most of the desktop printers, scanners and faxes with MFDs where commercially and practicably appropriate.

- The introduction of print-management software to replace the PALMS print system and any locally-developed arrangements such as Cashkard.

- A modern and fast  printing and copying solution

- To gain capital savings by not replacing individual printers, copiers and scanners, and gain efficiencies from introducing one standardised, centrally managed contract and charging system.

| OBJECTIVE | MEASURE |
| --- | --- |
| A single contract with one supplier for MFD’s and print management software | Contract in place Delivery of the service. |
| The replacement of most of the desktop printers, scanners and faxes with MFDs | Reduction in number of desktop printers, scanners and faxes. (Supplier to provide management data) |
| The introduction of print-management software to replace the PALMS and Cashcard payment systems | Contract in place. Successful testing. Delivery of the service. |
| To improve customer satisfaction | Customer feedback in relevant internal surveys and National Student Survey. Feedback facility in the system. |

## Metrics

This project will improve student and staff experience by providing improved, consistent and more reliable self-service copying and printing facilities with additional scanning services.

| UG Students & Student Experience | 6. National Student Survey (performance across the 7 question areas) | Indirect |
| --- | --- | --- |
| Earned Income | Non Funding Council Income | Direct |

## SUSTAINABILITY ISSUES

Reduction in the number of desktop printers will reduce energy, heat output and printer cartridge consumption as well as eliminating the embedded energy (and therefore CO2) of capital replacement.  A University survey by the successful supplier will report on the current amount of equipment on campus (base line) and offer proposed plans to make reductions and efficiencies. The University does not currently understand what the base line figure is.  Once the plan has been agreed with the agreement of college managers / heads of departments / end users etc  initial savings and sustainability benefits will be reported and if future surveys are conducted the impact of the Self Service Print and copy project could be measured against the base line measured as part of this project.

The use of a managed (rules-based) software system will ensure / encourage that staff send print work to the most efficient and effective machine for finishing. The rules are yet to be agreed by the project board . The software system will also allow staff to pick up their work from any machine at any destination The software will also track users and usage enabling departments to encourage their users to be accountable for printing and copying, in terms of sustainability.

The review will include assessing the sustainability profile of any new equipment (MFD / Printers) and the impact on the environment before, during and after use, including energy consumption. This will be covered in the detailed tender specification.

The unified approach and application of a single print management software will enable ‘paperless’ scan to email, double-sided printing, reduce wastage and possibly direct bulk printing to more efficient devices.

Data Protection

The new system will allow documents to be held secure on MFDs before the owner actually prints them.

# Scope & Timescale of the Project

- Project Scope

To set in place a single contract with one supplier for a ‘managed print service’, under which all MFDs (and probably selected desktop printers) and print-management software are supported by that supplier.  Support includes implementation management, advice, replacement toner cartridges, repair, maintenance, new machines, management information, continuous improvement and so on.  Campus Services will lead the provision of the service by providing the service manager

Installation of new MFDs or contract management of existing MFDs at suitable agreed locations, with comprehensive integrated site back-office systems networked for central overview of consolidated and detail data about each MFD.

- Project Timescales

| Serial | Milestone | Resp | By |
| --- | --- | --- | --- |
| 1 | Prepare Spec for temp library copiers | John Malloch | 18th Aug 2010 |
| 2 | Further specification for library copiers | John Malloch | 27th Aug 2010 |
| 3 | Replace Library Copiers | John Malloch | 15th Sept 2010 |
| 4 | Consult with colleagues / depts. | PRJ | 21st Jan 2010 |
| 5 | First Project Group Meeting | PRJ | 21st Jan 2010 |
| 6 | Agree PID by GROUP | Group | 21st Jan 2010 |
| 7 | Agree scope of project by GROUP | Group | 21st Jan 2010 |
| 8 | "Arrange supplier "" experience gathering"" presentations | PRJ | 9th February 2010 |
| 9 | PID Submitted to TIG | PRJ | 26th February 2010 |
| 10 | PID Agreed by TIG |  | 26th February 2010 |
| 11 | Visit other institutions with similar solutions | Group | 18th March 2010 |
| 12 | SSPC Project Group Meeting | PRJ | 4th February 2010 |
| 13 | Finalise and agree functional specification | Group | 4th February 2010 |
| 14 | PID submitted to PCG | PRJ | 7th April 2010 |
| 15 | Board to sign off functional specification | Board | 9th April 2010 |
| 16 | Issue ITT / Further competition(inc building audit) Procurement stage 1 – Outline Bids requested from all framework providers (non price elements scored in stage 2) | PRJ / Procurement | 30th April 2010 |
| 17 | Evaluate tender returns and shortlist | PRJ/Procurement/Group | 7th May 2010 |
| 18 | Stage 2 – Detailed bids requested from Shortlisted providers who pass non-price elements resent phase 2 documents. | PRJ | 21st May 2010 |
| 19 | Evaluate Stage 2 Bids & Supplier presentations | PRJ/Procurement/Group/Board | 4th June 2010 |
| 20 | Supplier reference checks | Procurement | 11th June 2010 |
| 21 | Preferred Bidder Decided & Board sign off | Board | 18th June |
| 22 | Mandatory Standstill |  | 2nd July 2010 |
| 23 | Set up and testing | PRJ | 20th August 2010 |
| 24 | Test the print management system through a coordinated phased implementation (replacement for PALMS, Cashkard and any other relevant systems) | PRJ / IT | 20th August 2010 |
| 25 | Test the staff recharging system; | PRJ / IT | 6th August 2010 |
| 26 | Review Testing and Contract Award | PRJ / Board | 27th August 2010 |
| 27 | Audit of hardware on Streatham and St Lukes Campus equipment survey on current state and proposals for installation of MFD’s. Publish baseline statistics (nos, types, cost to purchase, cost to run, CO2 | Nominated supplier | 24th September 2010 |
| 28 | Audit Review and planned solutions and proposals | Group/Board | 8th Oct 2010 |
| 29 | Consultation on audit recommendations with stakeholders | PRJ | 28th Oct 2010 |
| 30 | SSPC audit & recommendations sign off | PRJ & stakeholders | 29th Oct 2010 |
| 31 | Hardware assigned / redeployed as per plan. The project roll out details and timescales are not yet agreed | PRJ/ Board / Stakeholders & nominated supplier | From the 1st November 2010 |
| 32 | Complete Introduction and declare ‘steady-state’; Hand-over to ‘University Service Provider ( Campus Services tbc)’ | Supplier | Dec 2010 |
| 33 | Based on the September campus equipment survey and MFD’s installed, report initial savings estimate to board | Supplier | Jan 2011 |
| 34 | Continue to manage and improve the distribution of MFDs and the provision of service | Supplier / University Service Provider |  |

- University Campuses

The project will form a universal approach to self service print and copy at the Streatham and St Luke’s campuses.  ASU at the Cornwall campus should also be in scope to support intra-school working.  Other associated organisations (such as the Guild, TCS, TDV and PCMD) may choose to participate.

- Project Phases

| Phase 1 | Library temporary solution |
| --- | --- |
| Scope: | To replace out of contract equipment with short term contract |
| Dates/Duration: | August 2009 |
| Deliverables: | New MFD in place |
| Provided by: | John Malloch |

| Phase 2 | Project definition |
| --- | --- |
| Scope: | Scoping and defining the project, agreeing resources, timescales and finances |
| Dates/Duration: | Jan 2010 |
| Deliverables: | PID, Project Plan |
| Provided by: | Project Manager |

| Phase 3 | Consultation, Research and prepare specification |
| --- | --- |
| Scope: | Consultation and benchmarking |
| Dates/Duration: | Jan 2010 – March 2010 |
| Deliverables: | Working group have an understanding of other print and copy systems. Project communication plan in place. |
| Provided by: | Working Group and Project Manager |

| Phase 4 | Procurement |
| --- | --- |
| Scope: | Finalise functional specification, tender and award contract. |
| Dates/Duration: | April – August 2010 |
| Deliverables: | Procurement Services is fully engaged with this project. The recommended approach is to invite tenders (as part of a ‘mini-competition’) within an OGC framework agreement, which will provide pre-negotiated robust arrangements and flexibility to accommodate our specific requirements within a relatively fast process. The most important element will be the development of a clear ‘output’ specification, which will explain what we want to achieve. From this we can develop a scoring system and the appropriate tests or checks to ensure we get what we have specified. We suggest that part of the selection process should be that bidding suppliers review one school or a part of that school to suggest a solution that the UoE can assess. |
| Provided by: | Procurement |

| Phase 5 | Testing and contract award |
| --- | --- |
| Scope: | Hardware and software is tested by University IS department |
| Dates/Duration: | July & August 2010 |
| Deliverables: | Successful testing and contract award |
| Provided by: | IS / CaS |

| Phase 6 | Estate Audit |
| --- | --- |
| Scope: | Successful bidder audits current estate and makes recommendations |
| Dates/Duration: | September 2010 |
| Deliverables: | A) Robust plan in place in terms of machine type and number per location / building. B) Agreed with each school manager and Campus Services C) Implementation roll out plan in place D) Proposed savings to be outlined by supplier (short term savings and longer term savings) once implementation plan has been agreed. |
| Provided by: | Successful bidder |

| Phase 7 | Installation |
| --- | --- |
| Scope: | Start of planned and progressive roll out of MFD |
| Dates/Duration: | From November 2010 – The project roll out details and timescales are not yet finalised with new supplier or stakeholders ( see note 1 below) |
| Deliverables: | New MFD’s successfully and progressively rolled out and in use as per agreed plan (phase 4) Note 1 The introduction of the new contract, devices and software to more than 20 departments and organisations could take up to 12 months, and will depend on the state of each department’s current printing and copying contracts. For many departments, a speedy implementation may not be necessary because they have a working system that can run concurrently with the new contract. However, some schools have indicated strongly that they want to be early adopters for local reasons (expansion, current contracts, etc). As part of the roll-out the supplier will provide the initial “end-user” training for each department. Campus Services will provide ad-hoc training and support. Clear communication plan to inform end users on new practices, rules based printing, billing etc. Formal review following on from each installation |
| Provided by: | Campus Services & Successful bidder |

| Phase 8 | Project Closure and handover to operational management |
| --- | --- |
| Scope: | Closure of the project and handover to live operation, and ongoing supplier management. To agree ongoing project board to review and monitor the contract. |
| Dates/Duration: | Dec 31st 2010 |
| Deliverables: | Successful implementation and handover of the new MFDs. Support strategy Post-implementation report including review of savings, efficiencies, capital and revenue purchase avoidance, duplex printing, paper usage, CO2 saving, energy usage, printer numbers (space release), etc. Post award project board assigned |
| Provided by: | Project Manager |

## 3.1	Related Projects

| Projects | Expected Impact/ Completion Date |
| --- | --- |
| Network Upgrade project Infrastructure projects & New Buildings College transition Finance coding changes due to new aptos codes and changes within departments (e.g College transition) The Forum and any associated consideration that this project will be delivering MFD’s etc into it EDM System | Little impact. Co-ordination required with network team. Communicate aims of project with EDS Some impact at the time of transition because college managers and administrators will be focusing on mergers. Little impact as finance partners are involved in the project Clear communication of the project to the Forum project team and ensure that the working group are involved in any proposals. Little impact as MFD’s will scan to file/email. Ensure PM is aware of SSPC project |

## Out of Scope

- This project does not cover the development of a University smart card, other than the ability to accept them and collect payment (future proofing) if appropriate and possible.

# RISKS, constraints and ASSUMPTIONS

## 4.1	Risks

See Appendix A – Risk, Issues and Actions Log

## Constraints & Dependencies

- Network access

- Network access in suitable positions within buildings.

## Assumptions

The project will put a strong reliance on the chosen supplier to provide an all embracing solution within the contract.  These types of solution are common within the sector and across general business.  The specification will have to ensure that our requirements are clearly articulated.  The stakeholders on the working group (refer to paragraph 5.2.2) have all expressed their commitment to a good working solution.

# ReSource for the Project

## 5.1	Finance

- Capital Expenditure

The project will not incur any direct capital expenditure, however some costs may be incurred such as networking costs if the network points are in the wrong areas.  It is anticipated that such costs would not be borne from the project but by the University Service provider (Campus Services tbc) as an operational cost.

- Revenue Expenditure

The resulting contract will be based on pay-per-copy charging which will cover all associated costs such as operational management of the service, servicing, maintenance and consumable items.  (The handling of paper costs will be determined in due course.)

- Source of Income

Self Service printing and copying currently provides income and net contribution to various department’s budget. The introduction of this project with one lead department will indicate that budgetary re-assessment will be needed to be taken into account to offset any potential loss of income to any affected department.

## Staffing Resources

5.2.1	Project Board

  - Staff.

- Implementation Manager		Phil Rees-Jones	Campus Services

- Asst Implementation Manager	Julie Brown		Campus Services

- Technical Adviser			Nigel Phillips		Campus Services

- Project Secretary			Sally Griffiths		Campus Services

  - Project Board.	Members of the board

| Person | Title | Role or Interest |
| --- | --- | --- |
| (a) | (b) | (c) |
| Geoff Pringle | Director of Campus Services | Chair.& Co Sponsor Lead Department. |
| Deborah Welland | Assistant Director BISS | Co Sponsor |
| Phil Rees-Jones | Project Manager | Implementation |
| John Malloch | Head of Procurement | Procurement aspects |
| Mike Walton | Assistant Director, ICSD | ICSD/AS |
| Anna Verhamme | College Manager (Business School) | College’s perspective |
| Sue Hudson | Senior Project Manager | Assistant College Manager (Infrastructure and Technical Services) perspective |
| Jill Williams | Registrar Executive Officer | Customer perspective |

The Project Manager will provide all the paperwork and support for the meetings unless papers from other members are submitted.  The Chair will approve agendas and run the meeting ensuring agreement for items that require decisions are understood and agreed.

The project sponsor will normally chair the Project Board.  The sponsor’s role is to own the overall project.

The Project Board will make decisions which may involve change of scope, budget or timescales.

Standard Agenda Items for the Project Board are

- Minutes from previous meetings

- Risk/Issues/Actions Log

- Communications Plan

- Project Managers Report

    - Project Team

| Person | Title | Role or Interest |
| --- | --- | --- |
| (a) | (b) | (c) |
| Phil Rees-Jones | Project Manager | Chair. Representative of the Lead Department. |
| Richard Price | Contracts Officer, Procurement Services | Procurement |
| Nigel Weaver | Print Manager, St. Luke’s | St. Luke’s |
| Pete Bishop | ICSD | PALMS PC Clusters |
| Stephen Mossop | Head of Library Services | Library. Cashkard replacement. |
| Steve Grange | Head of Infrastructure | Infrastructure specialist |
| Julian Vinnels | Head of IT, PCMD | PCMD |
| Martin Henson | Finance & Systems team, Corporate Services | Recharging and Finance |
| Nigel Phillips | Print Services Manager | Nigel Phillips is the technical adviser. |
| Julie Brown | CaS | Assistant to Implementation Manager |
| Paul Lightowlers | Head of Corporate Systems | Systems specialist and previous experience |

Weekly or bi weekly status reports should be circulated to all project team members to ensure everyone is aware of the progress of the project.

# Managing the Project

List the project management reports that will be produced:

- Project Initiation Document plus appendices

  - Risk Log

  - Issue Log

  - Action Logs

- Key Messages Document

- Communication Plan (May 2010 attached)

- Procurement Schedule (> £25k)

- Project plan

- Project status reports

- Post Project Evaluation  report

## 6.1	Issue Control

Issues arising will be discussed with the relevant project team members and controlled by the Project Manager. Escalation to the Project Sponsor will be as required by the Project Manager.

See Appendix A – Risk, Issues and Actions Log

## Actions Register

Actions are recorded in the minutes of the Project Board and Team meetings

See Appendix A – Risk, Issues and Actions Log

## Financial Control

No direct finance involved in funding the project

## 6.4	Information Management

Where will all the information be stored and made available?

Project Manager & In Tend software

# stakeholders

Please see attachments

  - Key Stakeholders

  - Communication Plan

# planning

See Project plan

# APPROVAL

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsors | Geoff Pringle and Deborah Welland |  |  |
| Project Customer | Geoff Pringle |  |  |
| Project Manager | Phil Rees-Jones |  |  |