## Sheet1
Theme (Why) | Ref. | Objective (What) | Action (How) | Timeline | Responsible | Accountable | Success measures and milestones | RAG rating | Actions /Evidence/Notes against this 24 month plan
Visibility | 1 | Showcase our technical skills | Develop individual website profiles for technical staff | 2019-06-01 | Website lead TS Business Partners (BPs) | Head of Service | 50% staff with up to date web profiles within 1 year; 90% within 2 years
| 2 | Communicate changes in technical staff to academics | Monthly technical bulletins contributed to academic staff meetings/newsletters | 2018-12-01 | Unit of activity managers | Technical Services BPs | All UoA managers distributing monthly updates within 6 months
| 3 | Build a sense of community | Develop opportunities to better understand work environments across the service with work-shadowing and lab-exchanges | 2018-06-01 | Unit of activity managers | Technical Services BPs | PDRs in summer 2018 have such opportunities built in for the year ahead. Success evaluated at next interim PDR
| 4 | Increase visibility of Experimental Officers | Build an EO network across the University | 2018-12-01 | Experimental Officers | Head of Service | EOs regularly meeting and communicating; supporting and sharing best practice.
| 5 | Promote the Technical Services Conference more widely | Invite academic staff and PhD students to the annual conference | 2019-06-01 | Chair of conference committee | Head of Service | Increased numbers of academic staff in attendance and PhD students
Recognition | 6 | Improve the name ‘technician’ from the perspective of students | Actively promote technical career pathways to students – outreach events, open days, careers events | 2020-06-01 | Unit of activity managers | Technical Services BPs | Improved partnership working with students and students moving into GBP roles in a wider number of disciplines.
| 7 | Improve transparency around contribution and authorship on peer-reviewed articles. | Develop a policy on co-authorship of Technical staff on papers with the DVC Research and Impact | 2020-06-01 | Head of Technical Services | Chief College Operations Officer | Transparent guidelines in place that take into account expectations on behalf of the technician, academic and publisher
| 8 | Continue to promote reward and recognition schemes widely in the University | Promote A&B and the PSRAs to academic supervisors, particularly those of research technicians on fixed-term contracts | 2019-07-01 | Technical Services BPs | Head of Service
| 9 | Recognise Technical Services potential to contribute to the University’s international profile | Engage with international partnerships established to promote research and teaching links | 2018-12-01 | Technical Services BPs | Head of Service | Applications for internal international travelling fellowships put forward by technical staff.
| 10 | Increase the University’s technical services profile in the SW and nationally | Expand skills networks and EO networks beyond Exeter. | 2018-06-01 | Experimental Officers and Skills leads | Head of Service | Two SW skills networks launched at the TS conference in 2019
Career development | 11 | Develop professional networks external to the University | Implement a transparent and visible mechanism within TS to apply for funds to attend conferences | 2020-12-01 | Head of Technical Services | Chief College Operations Officer | At least 6 staff successfully applying for funds annually and sharing knowledge more widely on their return
| 12 | Provide an excellent PDR experience for every member of staff | Adopt ePDR in summer of 2018 | 2018-09-01 | All managers | Head of Service | 100% ePDR return and good quality feedback given in all cases
| 13 | Get the most out of the TS training budget | Consolidate training needs across the service through the ePDR system to provide an overview and enable the service training budget to be targeted the most effectively | 2019-06-01 | Technical Services BPs | Head of Service | TS training budget deployed more strategically and more staff recipients of training funds in each year
| 14 | Support staff to apply for roles at higher grades | When vacancies become available consider the advertisement of development roles – with clear progression from one grade | 2018-12-01 | Technical Services BPs | Head of Service | Examples of staff successful applying for development roles and moving up a grade over a set timeframe with the correct support in place
| 15 | Better prepare technical staff to apply and interview for new roles | Establish job application workshops and interview preparation sessions. | 2018-04-01 | Technical Services BPs and recruitment team | Head of Service | Termly job application workshops and individual interview prep sessions
Sustainability | 16 | Address single points of failure in skills and expertise | Use the EO network as a model to expand ‘skills networks’ across the service | 2019-06-01 | Nominated skills leads | Technical Services BPs | At least three skills networks established and running during first year
| 17 | Encourage increased numbers of staff to acquire professional qualifications | Work with the University’s apprenticeship team to enrol staff on CPD thus taking full advantage of the apprenticeship levy for technical staff | 2020-06-01 | Unit of Activity managers | Technical Services BPs | Treble number of staff on apprenticeship courses from 3 to 9 in first year and increase to 15 in year 2
| 18 | Ensure that this is a live action plan with progress monitoring and regular updates | Form a Technician’s Commitment Committee | 2018-09-01 | TC Committee Chair | Head of Service | TC committee launched, meeting termly and reporting on actions
| 19 | Develop opportunities for our students to gain experience in our working environments | Establish a programme of paid internships - promoting Technical Services as a career pathway | 2019-06-01 | Technical Services BPs | Head of Service | Internships established in at least one discipline per campus in the first year and 2 disciplines/campus by year 2.
| 20 | Make the most of our skills | Establish peer-to-peer training, particularly focused on research technicians on fixed term contracts | 2020-06-01 | Unit of activity managers and Experimental Officers | Technical Services BPs | Training sessions advertised and taken up in at least three specialisms in year 1, increasing to six in year 2